|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Activity | Activity Name | Activity Name Description | # of  Days | Start  Date  Dd/mm/yy | Dependency | Milestone |
| 1 | Planning |  | 11 | 14/02/14 |  |  |
| 1.1 | Conceptualization |  | 11 | 14/02/14 |  |  |
| 1.2 | Finding an advisor | Finding an appropriate advisor for the project | 2 | 17/02/14 |  |  |
| 1.3 | Finding a client | Looking for a client | 5 | 20/02/14 |  |  |
| 1.4 | Schedule Client Meeting | Setting a date for meeting the client | 2 | 20/02/14 |  |  |
| 1.5 | Problem Analyzation | Data gathering regarding the clients problems | 2 | 27/02/14 |  |  |
| 1.6 | Deciding application type | Deciding whether what type of application will be made. | 2 | 27/02/14 |  |  |
| 1.7 | Creation of Proposal | Created proposal to be passed to the client | 1 | 28/02/14 |  |  |
| 2 | Analysis |  | 130 | 03/03/14 |  |  |
| 2.1 | Collection of Data | Data gathering | 3 | 03/03/14 |  |  |
| 2.2 | Client Interview |  | 7 | 03/03/14 |  |  |
| 2.3 | Knowing the clients request |  | 3 | 12/03/14 |  |  |
| 2.4 | Create Event Table |  | 9 | 03/03/14 |  |  |
| 2.5 | Event Table |  | 1 | 13/03/14 |  |  |
| 2.6 | Presentation of Proposed Design |  | 8 | 08/08/14 |  |  |
| 2.7 | Presentation of Proposed System |  | 1 | 29/08/14 |  |  |
| 3 | Design | System Development | 8 | 17/03/14 |  |  |
| 3.1 | System Architecture |  | 3 | 17/03/14 |  |  |
| 3.2 | Screen Design | Finalizing website aesthetics and design | 5 | 20/03/14 |  |  |
| 4 | Development | System Development | 83 | 06/06/14 |  |  |
| 4.1 | Code | Code Sub-routine | 16 | 06/06/14 |  |  |
| 4.2 | Security | Adding website security | 68 | 27/06/14 |  |  |
| 4.3 | Shopping Cart Function | Implementation of items to be put on shopping cart | 37 | 03/07/14 |  |  |
| 4.4 | Login and Register Function | Implementation of the Login and Register | 28 | 01/07/14 |  |  |
| 4.5 | Input Website Content | Items to be sold are uploaded to the website | 1 | 06/06/14 |  |  |
| 5 | Testing | Prototype to be launch for clients recognition | 27 | 17/09/14 |  |  |
| 5.1 | Bug Fixes |  | 27 | 17/09/14 |  |  |
| 5.2 | Test Security | Testing web security if working correctly | 27 | 17/09/14 |  |  |
| 5.3 | Testing Complete | All functions to be tested for the clients to see | 1 | 23/10/14 |  |  |
| 6 | Implementation | Finalizing all systems function and systems design | 9 | 01/12/14 |  |  |
| 6.1 | Client Presentation | System to be presented to client for validation | 5 | 01/12/14 |  |  |
| 6.2 | Implement System |  | 4 | 06/12/14 |  |  |
| 6.3 | Project Complete |  | 1 | 11/12/14 |  | Completed System |